## Planned
Task ID | Task | Start Date | Time to Complete | Dependencies
1 | Process Journal | 1 | 13
2 | Planning Phase | 1 | 3
3 | Create the home page | 1 | 1 | 2
4 | Format the home page | 2 | 1 | 3
5 | Copy and Paste Each Page to create the basis for the other pages | 3 | 1 | 4
6 | Put Information into each page | 4 | 3 | 5
7 | Make Accordion on Anatomy of Computer | 4 | 2 | 4
8 | Create Maintenance and Toubleshooting Guide for PC | 5 | 3 | 5
9 | Research Parts for Frank's Gaming Café and add to Website | 8 | 2 | 5
10 | Add Drag and Drop to Website | 10 | 2 | 5
11 | Tidy Up the Website - Fix any mistakes | 12 | 2 | 1,2,3,4,5,6,7,8,9,10,11
12 | Evaluate Website | 14 | 1 | 10

## Actual
Task ID | Task | Start Date | Time to Complete | Dependencies
1 | Process Journal | 1 | 23
2 | Planning Phase | 1 | 3
3 | Create the home page | 1 | 1 | 2
4 | Format the home page | 1 | 11 | 3
5 | Copy and Paste Each Page to create the basis for the other pages | 2 | 1 | 4
6 | Put Information into each page | 12 | 3.5 | 5
7 | Make Accordion on Anatomy of Computer | 2 | 2 | 4
8 | Create Maintenance and Toubleshooting Guide for PC | 13 | 2 | 5
9 | Research Parts for Frank's Gaming Café and add to Website | 15 | 1 | 5
10 | Add Drag and Drop to Website | 15 | 3 | 5
11 | Tidy Up the Website - Fix any mistakes | 15 | 1 | 1,2,3,4,5,6,7,8,9,10,11
12 | Evaluate Website | 19 | 4 | 10